INDEPENDENT GUIDANCE FOR LAW FIRMS

Before you migrate: housekeeping and trial migration checklist

A checklist for law firms moving to a new practice management system, from planning and housekeeping through each trial migration to the final run. Whatever is open, half-finished or unexplained in the old system arrives that way in the new one, so start early and sign off every stage on evidence. Lead shows who usually drives each item; the firm signs off everything. Adapt it to your project.

| PROJECT | TRIAL MIGRATION 1 DATE | MIGRATION OWNER |
| --- | --- | --- |

Lead:  Firm  ·  Vendor  ·  Both   (who usually drives each item; the firm signs off everything)

START EARLY

Plan the migration

Six to eight weeks before the first trial migration.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Migration approach agreed in writing: full history or opening balances, and where historic data will be kept | Both |  |  |
| ☐ | Scope agreed for each trial: the accounts in the first; the accounts again plus agreed custom data and documents in the second | Both |  |  |
| ☐ | A migration owner named on the firm’s side, with the time to do it; the COFA involved from the start | Firm |  |  |
| ☐ | Data extract requested from the current supplier: format, timing and any cost agreed | Firm |  |  |
| ☐ | Reports to save at each trial cut-off date agreed | Both |  |  |
| ☐ | Shared issue log set up: an owner, a decision and a retest for every problem | Both |  |  |
| ☐ | Decisions on data (how records are split, how balances are treated) logged, with an agreed turnaround | Both |  |  |

HOUSEKEEPING  ·  1

Client and office account

Everything reconciled and explained before the data is taken.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Every office and client bank account reconciled, with as few outstanding items as possible | Firm |  |  |
| ☐ | No client ledgers in debit | Firm |  |  |
| ☐ | Suspense and holding ledgers emptied, each item posted to its proper matter | Firm |  |  |
| ☐ | Residual balances on closed matters returned or dealt with under the SRA Accounts Rules | Firm |  |  |
| ☐ | Unbanked receipts banked or reversed; old unpresented cheques chased, cancelled or written back | Firm |  |  |
| ☐ | Unidentified receipts traced and posted to the right matter | Firm |  |  |
| ☐ | Costs for agreed bills transferred from client to office account | Firm |  |  |
| ☐ | Old unreconciled items and half-completed transfers resolved | Firm |  |  |

HOUSEKEEPING  ·  2

Bills, time and disbursements

Only bring across what is real and collectable.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Draft and unposted bills posted or deleted | Firm |  |  |
| ☐ | Part payments and payments on account allocated to the right bills | Firm |  |  |
| ☐ | Agreed credit notes raised and linked to their bills | Firm |  |  |
| ☐ | Bad debts written off rather than migrated | Firm |  |  |
| ☐ | Unpaid invoices in the accounts package match the practice system | Firm |  |  |
| ☐ | Unrecoverable work in progress written off; non-chargeable time recorded as non-chargeable | Firm |  |  |
| ☐ | Unpaid supplier invoices paid or cancelled; estimated disbursements that will never arise cleared | Firm |  |  |
| ☐ | Fee earner and matter rates checked | Firm |  |  |

HOUSEKEEPING  ·  3

Contacts, matters and documents

The structure every workflow, precedent and report will rely on.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Duplicate contacts merged | Firm |  |  |
| ☐ | Records reshaped to fit how the new system models people and organisations (for example, joint records) | Firm |  |  |
| ☐ | Key details complete on active clients | Firm |  |  |
| ☐ | Finished matters closed; dormant matters reviewed | Firm |  |  |
| ☐ | Every open matter has a current fee earner and supervisor; leavers’ matters reassigned | Firm |  |  |
| ☐ | Matter types and departments correct, because they drive workflows, precedents and reports | Firm |  |  |
| ☐ | Emails and documents in personal folders filed to their matters; duplicates removed | Firm |  |  |
| ☐ | Custom transaction types, unusual entries and problem ledgers declared to the vendor | Firm |  |  |
| ☐ | Connected services listed for reconnection: searches, e-signature, payments, accounts package | Firm |  |  |

TRIAL MIGRATION 1

Trial migration 1: the accounts

The money comes first, because it has to be right to the penny.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Cut-off reports saved from the old system: client balances by matter, office balances, aged debtors, unbilled time and disbursements, bank reconciliations | Firm |  |  |
| ☐ | Accounts migrated | Vendor |  |  |
| ☐ | Validated with the trial migration validation checklist: headline figures, matter by matter, and a spot-check sample | Both |  |  |
| ☐ | Reconciled matter by matter against the cut-off reports, not just in total | Both |  |  |
| ☐ | Every difference logged with an owner, a decision and a retest | Both |  |  |
| ☐ | Results reviewed within the agreed window | Firm |  |  |
| ☐ | Findings reviewed by the COFA | Firm |  |  |

TRIAL MIGRATION 2

Trial migration 2: accounts again, plus custom data and documents

Prove the fixes held, and that everything works together.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Fixes from the first trial applied; accounts reconciled again to prove they held | Both |  |  |
| ☐ | Agreed custom data in the right fields | Both |  |  |
| ☐ | Documents and emails linked to the right matters, with access controls intact | Both |  |  |
| ☐ | Fee earners check their own live matters: custom data, key dates, documents | Firm |  |  |
| ☐ | Precedents generated and workflows run on migrated matters, including matters part way through a process | Both |  |  |
| ☐ | No new scope added without the time to map and test it | Both |  |  |
| ☐ | Accounts signed off by the COFA | Firm |  |  |

FINAL MIGRATION

Ready for the final migration

Then follow the one-month countdown checklist to go-live.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Housekeeping repeated for anything new since the trials | Firm |  |  |
| ☐ | Final migration rehearsed to the cut-over timetable | Vendor |  |  |
| ☐ | Written go or no-go criteria agreed | Both |  |  |
| ☐ | Read-only access to the old system arranged for queries and the accountant’s report | Firm |  |  |
| ☐ | One-month countdown checklist started (pclt.co.uk/downloads/one-month-go-live-countdown.docx) | Both |  |  |

Planning a migration? We help firms plan and run their housekeeping, manage the vendor through each trial migration, and make sure every stage is signed off on evidence. Truly independent, with no vendor ties. advice@pclt.co.uk ¦ pclt.co.uk

From the insight “Before you migrate: housekeeping, trial migrations and sign-off” at pclt.co.uk/insights/before-you-migrate-housekeeping-and-trial-migrations.html. General guidance only; adapt it to your own project and contracts.