INDEPENDENT GUIDANCE FOR LAW FIRMS

Go or no-go decision sheet

Use this at the go or no-go meeting before the final migration. Agree the criteria in writing weeks in advance, then judge each one on evidence, not on confidence. A criterion is met, met with a workaround the firm has accepted in writing, or not met. The decision and its conditions are recorded here.

| PROJECT | PLANNED GO-LIVE DATE | MEETING DATE | CHAIR |
| --- | --- | --- | --- |

STEP 1  ·  THE CRITERIA

Is each criterion met?

Tick one box for each. Record the evidence you looked at, not just that it exists.

Accounts and data

| Criterion | Evidence | Met | Work-around | Not met | Owner |
| --- | --- | --- | --- | --- | --- |
| Final trial migration reconciled matter by matter, and the accounts signed off by the COFA | Validation checklist | ☐ | ☐ | ☐ |  |
| Trial migration issues closed, or accepted with a workaround | Issue log | ☐ | ☐ | ☐ |  |
| Client and office bank reconciliations agree in both systems at the trial cut-off | Reconciliations | ☐ | ☐ | ☐ |  |
| Custom data, key dates and documents checked by the people who own the matters | Spot-check sample | ☐ | ☐ | ☐ |  |

The system

| Criterion | Evidence | Met | Work-around | Not met | Owner |
| --- | --- | --- | --- | --- | --- |
| User acceptance testing signed off | UAT sign-off | ☐ | ☐ | ☐ |  |
| Every case type and workflow tested end to end, on new and migrated matters | Test log | ☐ | ☐ | ☐ |  |
| Precedents generate correctly from migrated data | Test log | ☐ | ☐ | ☐ |  |
| Client and matter inception tested as one process, including ID and AML checks | Test log | ☐ | ☐ | ☐ |  |
| Integrations working: accounts package, email and Outlook, e-signature, searches, payments | Test log | ☐ | ☐ | ☐ |  |
| Key reports produce figures the partners, accounts team and compliance officers recognise | Report sign-off | ☐ | ☐ | ☐ |  |
| Users, roles and permissions set up; multi-factor authentication on; no accounts for leavers | User list | ☐ | ☐ | ☐ |  |

Risk and compliance

| Criterion | Evidence | Met | Work-around | Not met | Owner |
| --- | --- | --- | --- | --- | --- |
| Configuration reviewed by the COLP and COFA against the risk register and policies | Review notes | ☐ | ☐ | ☐ |  |
| Client account controls, ethical walls and audit trails working | Test log | ☐ | ☐ | ☐ |  |
| Every key date has an owner and has been checked | Key date report | ☐ | ☐ | ☐ |  |

People

| Criterion | Evidence | Met | Work-around | Not met | Owner |
| --- | --- | --- | --- | --- | --- |
| End users trained on the live configuration, by role | Training register | ☐ | ☐ | ☐ |  |
| Super-users named and ready in every team | Names | ☐ | ☐ | ☐ |  |
| Staff know the go-live timetable, where to get help and how to report a problem | Communications | ☐ | ☐ | ☐ |  |

Cut-over and support

| Criterion | Evidence | Met | Work-around | Not met | Owner |
| --- | --- | --- | --- | --- | --- |
| Cut-over timetable agreed, with named people on both sides | Cut-over plan | ☐ | ☐ | ☐ |  |
| Old system: posting stop time agreed, final extract arranged, read-only access in place afterwards | Cut-over plan | ☐ | ☐ | ☐ |  |
| Vendor go-live support confirmed: extra support, people on site or on call, escalation route | Support plan | ☐ | ☐ | ☐ |  |
| Support booked for the first bill run, first month-end and first client account reconciliation | Support plan | ☐ | ☐ | ☐ |  |
| Fallback plan agreed: what would make us stop, by when, and how we return to the old system | Fallback plan | ☐ | ☐ | ☐ |  |

Open issues

| Criterion | Evidence | Met | Work-around | Not met | Owner |
| --- | --- | --- | --- | --- | --- |
| No open issue that affects client money, key dates or the ability to work | Issue log | ☐ | ☐ | ☐ |  |
| Every other open issue has an owner, a workaround and a fix date | Issue log | ☐ | ☐ | ☐ |  |

STEP 2  ·  OPEN ISSUES

Open issues carried into go-live

Anything not fully fixed, with its workaround. Nothing here should touch client money or key dates.

| Issue no. | Description | Severity | Workaround | Owner | Fix date |
| --- | --- | --- | --- | --- | --- |

STEP 3  ·  THE DECISION

Decision

Go: every criterion is met, or met with a workaround the firm has accepted in writing.

Go with conditions: only where the conditions are specific, owned, dated and do not touch client money or key dates.

No-go: any criterion on client money, key dates or the ability to work is not met. Set a new date and the evidence needed to meet it.

☐ Go        ☐ Go with conditions        ☐ No-go        New date if no-go: ______________

CONDITIONS (WHAT, WHO, BY WHEN)

FALLBACK TRIGGER: WHAT WOULD MAKE US STOP, AND THE LATEST TIME TO DECIDE

STEP 4  ·  SIGN-OFF

Signed on behalf of the firm and the vendor

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project sponsor or managing partner |  |  |  |
| Firm’s project manager |  |  |  |
| COFA |  |  |  |
| COLP |  |  |  |
| Vendor’s project manager |  |  |  |

Want an independent chair for the decision? We act as the firm’s project manager or work alongside it, so the decision to go live is made on evidence, not momentum. Truly independent, with no vendor ties. advice@pclt.co.uk ¦ pclt.co.uk

From the insight “One month before go-live” at pclt.co.uk/insights/one-month-before-go-live.html. Use it with the one-month countdown checklist. General guidance only; adapt the criteria to your own project and contracts.