INDEPENDENT GUIDANCE FOR LAW FIRMS

One month to go-live: countdown checklist

A week-by-week checklist for the last month before a new practice management system goes live, and the first weeks after. One month out, the build should be finished: the final month is for training people on the system they will use on day one, with changes kept to a minimum. Lead shows who usually drives each item; the firm signs off everything. Adapt it to your project.

| PROJECT | GO-LIVE DATE | CHECKLIST OWNER |
| --- | --- | --- |

Lead:  Firm  ·  Vendor  ·  Both   (who usually drives each item; the firm signs off everything)

COUNTDOWN  ·  WEEK 4

Four weeks out: the readiness checkpoint

If several of these are not done, decide now whether to move the date.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | User acceptance testing complete and signed off; every defect fixed and retested, or accepted in writing with a workaround and a date | Firm |  |  |
| ☐ | Trial migrations complete; accounts reconciled matter by matter against reports from the old system and signed off by the COFA | Both |  |  |
| ☐ | Custom data, key dates and documents checked by the people who own the matters | Firm |  |  |
| ☐ | Every case type and workflow tested end to end, on new matters and on migrated matters part way through a process | Both |  |  |
| ☐ | Precedents generate correctly from migrated data | Firm |  |  |
| ☐ | Client and matter inception tested as one process: enquiry, conflict search, ID and AML checks, engagement letter, matter risk assessment, opening | Firm |  |  |
| ☐ | Configuration reviewed against the risk register and policies by the COLP and COFA: client account controls, key dates, supervision and file reviews, permissions and ethical walls, audit trail, breach register | Firm |  |  |
| ☐ | Integrations tested with real scenarios: accounts package, email and Outlook, e-signature, searches, payments | Both |  |  |
| ☐ | Key reports validated by partners, the accounts team and compliance officers | Firm |  |  |
| ☐ | Users set up with the right roles, multi-factor authentication on, no accounts for leavers | Both |  |  |
| ☐ | Cut-over plan written: timetable, named people on both sides, fallback if it goes wrong | Vendor |  |  |
| ☐ | Written go or no-go criteria agreed | Both |  |  |
| ☐ | Date for the old system’s final data extract confirmed with the outgoing supplier | Firm |  |  |
| ☐ | Change freeze starts: defect fixes only, every other request goes on the after go-live list | Both |  |  |

COUNTDOWN  ·  WEEKS 3 AND 2

Weeks three and two: training and rehearsal

Train on the live configuration, not a demonstration system.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | End-user training by role, using the tasks each person actually does, on the day-one configuration | Vendor |  |  |
| ☐ | Training environment and data match the live configuration | Vendor |  |  |
| ☐ | Super-users named in each team and trained first | Firm |  |  |
| ☐ | Practice time booked for every user after their training | Firm |  |  |
| ☐ | Dress rehearsal of the final migration to the cut-over timetable | Vendor |  |  |
| ☐ | Issue log reviewed jointly at least weekly; nothing open without an owner and a date | Both |  |  |
| ☐ | Housekeeping in the old system finished: bank accounts reconciled, drafts posted or deleted, payments allocated, suspense cleared | Firm |  |  |
| ☐ | Clients and third parties told about anything that changes for them (payment links, portals, document formats) | Firm |  |  |
| ☐ | Go-live support confirmed: extra support in the first weeks, people on site or on call, escalation route | Vendor |  |  |
| ☐ | Support booked for the first bill run, first month-end and first client account reconciliation | Vendor |  |  |
| ☐ | Read-only access to the old system arranged for queries and the accountant’s report | Firm |  |  |

COUNTDOWN  ·  WEEK 1

The final week: cut-off

Stop new activity in the old system and capture the figures the new one will be checked against.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Issue log reviewed daily | Both |  |  |
| ☐ | Fee earners finish recording time and costs | Firm |  |  |
| ☐ | Final bills and receipts of the period posted | Firm |  |  |
| ☐ | Last bank reconciliation completed for every office and client account | Firm |  |  |
| ☐ | Cut-off reports saved: client balances by matter, office balances, aged debtors, unbilled time and disbursements, bank reconciliations | Firm |  |  |
| ☐ | Go or no-go meeting held against the written criteria, using the go or no-go decision sheet; decision recorded | Both |  |  |
| ☐ | Posting stops in the old system; final extract taken | Both |  |  |

DAY ONE

Go-live

Check the things that matter most before people start work.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Final migration run and accounts reconciled matter by matter against the cut-off reports; COFA sign-off | Both |  |  |
| ☐ | Key workflows, precedents and integrations smoke-tested on live data | Both |  |  |
| ☐ | Every user can sign in with multi-factor authentication | Both |  |  |
| ☐ | Super-users and support on the floor or on call | Both |  |  |
| ☐ | Staff told the system is live, where to get help and how to report a problem | Firm |  |  |

AFTER GO-LIVE

The first four weeks

Stay close: small problems found early stay small.

| Done | Item | Lead | Owner | Due |
| --- | --- | --- | --- | --- |
| ☐ | Daily check-in with the vendor in the first week, then weekly | Both |  |  |
| ☐ | First bills produced and checked | Firm |  |  |
| ☐ | First client account reconciliation completed and signed off within the SRA timeframe | Firm |  |  |
| ☐ | First month-end completed | Firm |  |  |
| ☐ | After go-live list reviewed and prioritised; changes scheduled, not rushed | Both |  |  |
| ☐ | Lessons learned recorded while they are fresh | Both |  |  |

Going live soon? We act as the firm’s project manager or work alongside it: setting the readiness checkpoint, managing the vendor through the last month and making sure the decision to go live is made on evidence. Truly independent, with no vendor ties. advice@pclt.co.uk ¦ pclt.co.uk

From the insight “One month before go-live” at pclt.co.uk/insights/one-month-before-go-live.html. General guidance only; adapt it to your own project and contracts.